## Azure Devops(Cognizant)
Questionnaire - Knowledge Acquisition Phase Azure Devops
|  |  | Owner |  |  | Cognizant Devops Transition Status
Sr. No. | Topics | Mode of KT | Cognizant SME | Uniper SME | Wipro SME | Status | Target Completion Date | Actual Completion Date | Wiki Link | Document Location | Remark
S-1 | Session-1 : General discussion on client environment.
A-1 | Understanding Business and organization | Remote | Vamshi / Ashok | Schmitz Carsten | Rajiv Mishra | Completed | 2022-04-05 | 2022-03-30 | https://wiki.intranet.uniper.energy/sales/display/CF/Guidelines | Uniper Confluence page | Cognizant
A-2 | Azure Boards | Remote | Vamshi / Ashok | Schmitz Carsten | Rajiv Mishra | Completed | 2022-04-05 | 2022-03-30 | https://wiki.intranet.uniper.energy/sales/display/CF/Azure+DevOps+Billing | Uniper Confluence page | Cognizant
A-3 | how we are creating the work items/tasks in Azure Boards | Remote | Vamshi / Ashok | Schmitz Carsten | Rajiv Mishra | Completed | 2022-04-05 | 2022-03-30 | https://wiki.intranet.uniper.energy/sales/display/CF/Build+and+release+agents | Uniper Confluence page | it will be done by Uniper lead(Carsten)
A-4 | Tracking the work items using Azure Boards. | Remote | Vamshi / Ashok | Schmitz Carsten | Rajiv Mishra | Completed | 2022-04-05 | 2022-03-30 | https://wiki.intranet.uniper.energy/sales/display/CF/Azure+DevOps+Billing | Uniper Confluence page | it will be done by Uniper lead(Carsten)
A-5 | Azure DevOps Integration into Azure | Remote | Vamshi / Ashok | Schmitz Carsten | Rajiv Mishra | Completed | 2022-04-05 | 2022-03-30 | https://wiki.intranet.uniper.energy/sales/display/CF/Azure+DevOps+Integration+into+Azure | Uniper Confluence page | Cognizant
A-6 | Custom code repository and code implementation? | Remote | Vamshi / Ashok | Schmitz Carsten | Rajiv Mishra | Completed | 2022-04-05 | 2022-03-30 | https://wiki.intranet.uniper.energy/sales/display/CF/FAQ%3A+Azure+DevOps | Uniper Confluence page | Cognizant
A-7 | Understanding the Sprint planning. | Remote | Vamshi / Ashok | Schmitz Carsten | Rajiv Mishra | Completed | 2022-04-05 | 2022-03-30 | https://wiki.intranet.uniper.energy/sales/display/THO/PI+and+Sprint+Planning%2C+Step+by+Step | Uniper Confluence page | Cognizant
A-8 | Azure Git Repositories | Remote | Vamshi / Ashok | Schmitz Carsten | Rajiv Mishra | Completed | 2022-04-05 | 2022-03-30 | https://wiki.intranet.uniper.energy/sales/display/CF/Uniper+GitHub+Action+and+Azure+Integration | Uniper Confluence page | Cognizant
A-9 | How many Azure repos we have in Uniper | Remote | Vamshi / Ashok | Schmitz Carsten | Rajiv Mishra | Completed | 2022-04-05 | 2022-03-30 | https://wiki.intranet.uniper.energy/sales/display/CF/Azure-DevOps+Integration+with+AKS+Cluster?searchId=YGBZF4KRN | Uniper Confluence page | This will be taken care by application team
A-10 | Understand the Branching Strategies. | Remote | Vamshi / Ashok | Schmitz Carsten | Rajiv Mishra | Completed | 2022-04-05 | 2022-03-30 | https://wiki.intranet.uniper.energy/sales/display/CF/Uniper+GitHub+Best+Practices?searchId=2KS1JZONN | Uniper Confluence page | This will be taken care by application team
A-11 | Understand the Branching Policies. | Remote | Vamshi / Ashok | Schmitz Carsten | Rajiv Mishra | Completed | 2022-04-05 | 2022-03-30 | https://wiki.intranet.uniper.energy/sales/display/CF/Uniper+GitHub+Best+Practices?searchId=2KS1JZONN | Uniper Confluence page | This will be taken care by application team
A-12 | Azure Pipelines | Remote | Vamshi / Ashok | Schmitz Carsten | Rajiv Mishra | Completed | 2022-04-05 | 2022-03-30 | https://wiki.intranet.uniper.energy/sales/display/CF/How+to+build+your+Pipeline+in+Azure+Devops | Uniper Confluence page | Cognizant
A-13 | Which type of pipeline we are using classic or yaml ? | Remote | Vamshi / Ashok | Schmitz Carsten | Rajiv Mishra | Completed | 2022-04-05 | 2022-03-30 | https://wiki.intranet.uniper.energy/sales/pages/viewpage.action?pageId=82511387&searchId=993BUU6FI | Uniper Confluence page | This will be taken care by application team
A-14 | which type of agent pool we are using Microsoft hosted or self hosted ? | Remote | Vamshi / Ashok | Schmitz Carsten | Rajiv Mishra | Completed | 2022-04-05 | 2022-03-30 | https://wiki.intranet.uniper.energy/sales/display/CF/Microsoft+Defender+for+Cloud?searchId=H223XCC1O | Uniper Confluence page | This will be taken care by application team
A-15 | Understand the complete CICD flow. | Remote | Vamshi / Ashok | Schmitz Carsten | Rajiv Mishra | Completed | 2022-04-05 | 2022-03-30 | https://wiki.intranet.uniper.energy/sales/display/CF/How+to+build+your+Pipeline+in+Azure+Devops | Uniper Confluence page | This will be taken care by application team
A-16 | How we are managing service connections? | Remote | Vamshi / Ashok | Schmitz Carsten | Rajiv Mishra | Completed | 2022-04-05 | 2022-03-30 | https://wiki.intranet.uniper.energy/sales/pages/viewpage.action?pageId=44004131&searchId=SACB833RT | Uniper Confluence page | Cognizant
A-17 | Azure Test plans & Azure Artifacts | Remote | Vamshi / Ashok | Schmitz Carsten | Rajiv Mishra | Completed | 2022-04-05 | 2022-03-30 | https://wiki.intranet.uniper.energy/sales/display/CF/Uniper+GitHub+Action+and+Azure+Integration?searchId=EJWZ83F96 | Uniper Confluence page | Cognizant
A-18 | Understand the TestPlanes. | Remote | Vamshi / Ashok | Schmitz Carsten | Rajiv Mishra | Completed | 2022-04-05 | 2022-03-30 | https://wiki.intranet.uniper.energy/sales/display/CF/Azure+DevOps+Git+integration?searchId=YGBZF4KRN | Uniper Confluence page | This will be taken care by application team
A-19 | How many people are currently performing the work on this Azure Devops? | Remote | Vamshi / Ashok | Schmitz Carsten | Rajiv Mishra | Completed | 2022-04-05 | 2022-03-30 | https://wiki.intranet.uniper.energy/sales/display/CF/New+Azure+DevOps+Project+Creation+process+-+User+Guide?searchId=48VKXVBYT | Uniper Confluence page | This will be taken care by application team
A-20 | Working with Test cases. | Remote | Vamshi / Ashok | Schmitz Carsten | Rajiv Mishra | Completed | 2022-04-05 | 2022-03-30 | https://wiki.intranet.uniper.energy/sales/display/CF/DevOps+-+Assign+license+to+User+for+billable+extensions?searchId=FE29RPVF5 | Uniper Confluence page | This will be taken care by application team
A-21 | What is the frequency of Customer Meetings/Reviews? | Remote | Vamshi / Ashok | Schmitz Carsten | Rajiv Mishra | Completed | 2022-04-05 | 2022-03-30 | https://wiki.intranet.uniper.energy/sales/display/CF/HaCT+DevOps+Framework?searchId=T7H82F8L3 | Uniper Confluence page | Cognizant
A-22 | How do you interact with the customer to provide updates/reviews? | Remote | Vamshi / Ashok | Schmitz Carsten | Rajiv Mishra | Completed | 2022-04-05 | 2022-03-30 | https://wiki.intranet.uniper.energy/sales/display/CF/HaCT+DevOps+Framework?searchId=T7H82F8L3 | Uniper Confluence page | Cognizant
A-23 | Creating & sharing packages. | Remote | Vamshi / Ashok | Schmitz Carsten | Rajiv Mishra | Completed | 2022-04-05 | 2022-03-30 | https://wiki.intranet.uniper.energy/sales/display/CF/Azure+Logic+apps?searchId=JJSENRVVY | Uniper Confluence page | This will be taken care by application team
A-24 | Publishing the packages to Azure Artifacts. | Remote | Vamshi / Ashok | Schmitz Carsten | Rajiv Mishra | Completed | 2022-04-05 | 2022-03-30 | https://wiki.intranet.uniper.energy/sales/display/CF/Uniper+GitHub+Action+and+Azure+Integration?searchId=FNG4JR2I4 | Uniper Confluence page | This will be taken care by application team
A-25 | Adding packages to pipeline. | Remote | Vamshi / Ashok | Schmitz Carsten | Rajiv Mishra | Completed | 2022-04-05 | 2022-03-30 | https://wiki.intranet.uniper.energy/sales/display/CF/How+to+build+your+Pipeline+in+Azure+Devops?searchId=G87PYU2A2 | Uniper Confluence page | This will be taken care by application team
A-26 | what is naminig conversion for services and different environments. | Remote | Vamshi / Ashok | Schmitz Carsten | Rajiv Mishra | Completed | 2022-04-05 | 2022-03-30 | https://wiki.intranet.uniper.energy/sales/display/CF/Naming+Convention?searchId=TPS6K8X5Q | Uniper Confluence page | Cognizant
S-2 | Session-2 : CLIENT / CONTACT GROUP INFORMATION
A-1 | Azure Organizational Configuration & Azure pipeline | Remote | Vamshi / Ashok | Schmitz Carsten | Rajiv Mishra | Completed | 2022-04-05 | 2022-03-31 | https://wiki.intranet.uniper.energy/sales/display/CF/How+to+build+your+Pipeline+in+Azure+Devops?searchId=W0KYZ2M5X | Uniper Confluence page | Cognizant
A-2 | ADO organizational configuration | Remote | Vamshi / Ashok | Schmitz Carsten | Rajiv Mishra | Completed | 2022-04-05 | 2022-03-31 | https://wiki.intranet.uniper.energy/sales/display/CF/Azure-DevOps+Integration+with+AKS+Cluster?searchId=IQ6OB5B2M | Uniper Confluence page | Cognizant
A-3 | Sonarcloud management | Remote | Vamshi / Ashok | Schmitz Carsten | Rajiv Mishra | Completed | 2022-04-05 | 2022-03-31 | https://wiki.intranet.uniper.energy/sales/display/CF/Azure+DevOps+and+Sonar+Cloud+Integration?searchId=LPNRXLU99 | Uniper Confluence page | Cognizant
A-4 | Automations like Logic apps and service connection | Remote | Vamshi / Ashok | Schmitz Carsten | Rajiv Mishra | Completed | 2022-04-05 | 2022-03-31 | https://wiki.intranet.uniper.energy/sales/display/CF/Azure+Logic+apps?searchId=UG2ATWEVZ | Uniper Confluence page | Cognizant
A-5 | Azure DevOps pipelines created and used by HACT | Remote | Vamshi / Ashok | Schmitz Carsten | Rajiv Mishra | Completed | 2022-04-05 | 2022-03-31 | https://wiki.intranet.uniper.energy/sales/pages/viewpage.action?pageId=44004709&searchId=ZXFQFJ8TI | Uniper Confluence page | Cognizant
S-3 | Session-3 : OTHER SERVICES IN UNIPER ENVIRONMENT
A-1 | GitHub & GitHub- service connection | Remote | Vamshi / Ashok | Schmitz Carsten | Rajiv Mishra | Completed | 2022-04-05 | 2022-04-12 | https://wiki.intranet.uniper.energy/sales/pages/viewpage.action?pageId=44004131&searchId=5ZQPS6WNK | Uniper Confluence page | Cognizant
A-2 | version control system | Remote | Vamshi / Ashok | Schmitz Carsten | Rajiv Mishra | Completed | 2022-04-05 | 2022-04-12 | https://wiki.intranet.uniper.energy/sales/pages/viewpage.action?pageId=35757915&searchId=O69SX7VJE | Uniper Confluence page | Cognizant
A-3 | Onboard new users | Remote | Vamshi / Ashok | Schmitz Carsten | Rajiv Mishra | Completed | 2022-04-05 | 2022-04-12 | https://wiki.intranet.uniper.energy/sales/display/CF/Add+User+on+Azure+DevOps?searchId=DI70W73AO | Uniper Confluence page | Cognizant
A-4 | Create new organizations | Remote | Vamshi / Ashok | Schmitz Carsten | Rajiv Mishra | Completed | 2022-04-05 | 2022-04-12 | https://wiki.intranet.uniper.energy/sales/display/CF/DevOps+-+Create+new+Azure+DevOps+project?searchId=08MERB58Q | Uniper Confluence page | Cognizant
A-5 | Wiki Documents | Remote | Vamshi / Ashok | Schmitz Carsten | Rajiv Mishra | Completed | 2022-04-05 | 2022-04-12 | https://wiki.intranet.uniper.energy/sales/display/CF/DevOps+-+Configure+Azure+DevOps+integration | Uniper Confluence page | Cognizant
A-6 | Azure Devops Demogenerator | Remote | Vamshi / Ashok | Schmitz Carsten | Rajiv Mishra / Martin | Planned | 2022-04-05 |  |  |  | Cognizant
A-7 | Storage tables | Remote | Vamshi / Ashok | Schmitz Carsten | Rajiv Mishra / Martin | Planned | 2022-04-05 |  |  |  | Cognizant
A-8 | ACR Tasks through Logic App automation | Remote | Vamshi / Ashok | Schmitz Carsten | Rajiv Mishra / Martin | Planned | 2022-04-05 |  |  |  | Cognizant
A-9 | ACR tasks and Unipercontainerregistry | Remote | Vamshi / Ashok | Schmitz Carsten | Rajiv Mishra | Completed | 2022-04-05 | 2022-04-12 | https://wiki.intranet.uniper.energy/sales/pages/viewpage.action?pageId=44003991&searchId=L71BC1AH5 | Uniper Confluence page | Cognizant
| Planned | 3 | [5 empty] | Reverse KT Planned
| In Progress | 0 | [5 empty] | Reverse KT In Progress
| Completed | 37 | 92.5% |  |  |  |  | Reverse KT Completed
| Delayed | 0 | [5 empty] | Reverse KT Delayed